Dr. Lennart Wittkuhn

# Timetable

* **Project period:** 01.04.2024 to 31.03.2025
* **Course delivery:** 14.10.2024 to 01.02.2025 (winter term)

| Step | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Preparation of new learning resources | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |  |  |
| Adaptation of existing resources to virtual setting | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |  |  |
| Continuous documentation and publication of all learning resources as OER | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |  |  |
| Preparation of questions for evaluation and self-assessment (quiz questions) in formR |  |  |  |  | Aug | Sep | Oct | Nov | Dec | Jan |  |  |
| Delivery of the courses |  |  |  |  |  |  | Oct | Nov | Dec | Jan |  |  |
| Analysis of the evaluation data and self-assessment (quiz questions) |  |  |  |  |  |  | Oct | Nov | Dec | Jan |  |  |
| Supervision of students in open office hours and via GitHub |  |  |  |  |  |  | Oct | Nov | Dec | Jan |  |  |
| Final analysis of the continuous teaching evaluations |  |  |  |  |  |  |  |  |  |  | Feb |  |
| Project evaluation and preparation of a results and experience report |  |  |  |  |  |  |  |  |  |  | Feb | Mar |
| Persistent archiving of all Open Educational Resources via e.g., Zenodo |  |  |  |  |  |  |  |  |  |  |  | Mar |